## Initial Work
|  |  | Main Tasks | Start Date | End Date | Reserved Days | Remaining Days | TODAY | 2025-02-04
1 |  |  | CAD functionalities (Import/Export - Closed Checking - Geometrical Queries)
1.1 |  |  | Finding the proper CAD Kernel (OCCT, Scad, CGAL, Sumo) | 2025-02-05 | 2025-03-07 | 30 | 31
| 1.1.1 |  | Literature Research & Investigation of Similar Software | 2025-02-05 | 2025-03-07 | 30 | 31
1.2 |  |  | CAD Kernel Interface & Tests
| 1.2.1 |  | Import/Export Capability (Edge connectivity-Surface Representation)
| 1.2.2 |  | Part Geometry (Solid Operations-Boolean) - Farfield etc.
1.3 |  |  | Implementation to TAMS-Mesh (I/O formatting)
| 1.3.1 |  | Repairing the problems arised from exporting commercial CAD program
| 1.3.2 |  | Converting to the resultant geometry into the meshable geometry with queries
| 1.3.3 |  | Curve Modeling Implementations
| 1.3.4 |  | Surface Modeling Implementations
2 |  |  | Surface Meshing Algorithms Implementation
| 2.0.1 |  | C++ OOP skills + Workspace Prepreation
| 2.0.2 |  | Literature Research
| 2.0.3 |  | Examination of Existing Tools (more detailed)
2.1 |  |  | 1D Meshing
| 2.1.1 |  | Determination of Requirement Set
| 2.1.2 |  | Reqired 1D Input Format for 2D Mesh
| 2.1.3 |  | Implementation
2.2 |  |  | 2D Meshing
| 2.2.1 |  | Algorithm Literature/Tool Research
|  | 2.2.1.1 | Determination of Best Suitable Data Structure
|  | 2.2.1.2 | Triangulation Methods Investigation
|  | 2.2.1.3 | Is There any Existing Libraries
| 2.2.2 |  | Suitable algorithm designation and Implementation
3 |  |  | Optimization / Post-processing
| 3.1 |  | Optimization Method Research
| 3.2 |  | Quality Metrics Output Tools Implementation/Creation
| 3.3 |  | Basic Optimization Methods Implementation
4 |  |  | Export Methods (STL) CGNS Foam

## Project Template
TAMS MESH (Surface Mesher)
LITERATURE RESEARCH AND CODE REVIEW (UNDERSTANDING AVAILABLE OPENSOURCE GEOM MESH CODES)
Geometry |  | Mesher |  | PostProcessor |  | Platform
Geometric Features | 1D & 2D description of geometry for mesher | Algorithm | Generalized algoritm research for mesher
| Selection of best suitable geometry kernel |  | Selection of most suitable algorithm for CFD applications
| Identification of converter reqirement for mesher | Input Requirements | Required geometric expressions or objects for mesh generator
| [Depends] Converter coding challenges | 1D Meshing | Edge disreatization |  |  | Visualization Tool | Platform for development phase, visualization of geometric entities and mesh elements
Difficulty identification between 1D mesh and 2D mesh section
Selection of 1D domain disreatization methods required for CFD mesh
Coding challenges
|  |  | Automatization (minimum user input & overriding setup) | Optimization Methods | Identification of optimization tool reqirements for 1D mesh generation
|  | 2D Meshing | Reqired inputs prework for 2D surface meshing
2D Meshing Algorithm Needs | Identification of any geometric property need for 2D mesher inputs |  | [Depends] : Implementation of inputs into the mesher structure, coding challenges | Geometric Optimization | Prework for geometric property optimization needed or not, coding challenges [like tesellation]
| [Depends] : 2D mesher reqirement implementation to geometry properties, coding challenges |  | 2D meshing algorithm implementation to mesher, [main task, coding challenge] | Algoritm Based Optimization, Check Cycles | Optimization cycle development for valid, good quality and intended mesh, coding challenges
|  | Automatization | Automatization (minimum user input & overriding setup for all features relation between 1D and 2D overriding setup) |  | [Additional] Post Checkers
Additional Features | Basic geometrical operation for reparametrization geometry

## 2025 Gantt Chart
| TASK | ASSIGNED TEAM | PROGRESS | WORK EFFORT [WEEK] | EMPTY | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13 | WEEK 14 | WEEK 15 | WEEK 16 | WEEK 17 | WEEK 18 | WEEK 19 | WEEK 20 | WEEK 21 | WEEK 22 | WEEK 23 | WEEK 24 | WEEK 25 | WEEK 26 | WEEK 27 | WEEK 28 | WEEK 29 | WEEK 30 | WEEK 31 | WEEK 32 | WEEK 33 | WEEK 34 | WEEK 35 | WEEK 36 | WEEK 37 | WEEK 38 | WEEK 39 | WEEK 40 | WEEK 41 | WEEK 42 | WEEK 43 | WEEK 44 | WEEK 45 | WEEK 46 | WEEK 47 | WEEK 48 | WEEK 49 | WEEK 50 | WEEK 51 | WEEK 52
LITERATURE RESEARCH AND CODE REVIEW |  | NOT DEFINED | 0% | 1 AY + AS PROJECT
Geometry |  |  |  | 5 AY
Finding Proper Cad Kernel |  | NOT DEFINED | 0% | 0
| 1D & 2D description of geometry | NOT DEFINED | 0% | 0
| Import/Export Capability | NOT DEFINED | 0% | 0
| Repair tools | NOT DEFINED | 0% | 0
Implementation and I/O System |  | NOT DEFINED | 0% | 0
| Fixing Real Geometries | NOT DEFINED | 0% | 0
| Meshable Queries | NOT DEFINED | 0% | 0
| Curve & Surface Modeling | NOT DEFINED | 0% | 0
Mesher |  |  |  | 8 AY
Prework |  | NOT DEFINED | 0% | 0
| General algoritm research | NOT DEFINED | 0% | 0
| Most suitable algorithm | NOT DEFINED | 0% | 0
1D Meshing |  | NOT DEFINED | 0% | 0
| Requirement Set | NOT DEFINED | 0% | 0
| Implementation | NOT DEFINED | 0% | 0
2D Meshing |  | NOT DEFINED | 0% | 0
| Data Structures and Algorithms | NOT DEFINED | 0% | 0
| Implementation | NOT DEFINED | 0% | 0
| Automatization | NOT DEFINED | 0% | 0
Optimization |  |  |  | AS MESHER + 4 AY
| Optimization Method Research | NOT DEFINED | 0% | 0
| Post Optimization Implementation | NOT DEFINED | 0% | 0
Development Platform
| Tools for Development Phase | NOT DEFINED | 0% | 0
Export Methods
| CGNS / Foam | NOT DEFINED | 0% | 0

## 2026 Gantt Chart
TASK | ASSIGNED TEAM | PROGRESS | WORK EFFORT [WEEK] | EMPTY | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13 | WEEK 14 | WEEK 15 | WEEK 16 | WEEK 17 | WEEK 18 | WEEK 19 | WEEK 20 | WEEK 21 | WEEK 22 | WEEK 23 | WEEK 24 | WEEK 25 | WEEK 26 | WEEK 27 | WEEK 28 | WEEK 29 | WEEK 30 | WEEK 31 | WEEK 32 | WEEK 33 | WEEK 34 | WEEK 35 | WEEK 36 | WEEK 37 | WEEK 38 | WEEK 39 | WEEK 40 | WEEK 41 | WEEK 42 | WEEK 43 | WEEK 44 | WEEK 45 | WEEK 46 | WEEK 47 | WEEK 48 | WEEK 49 | WEEK 50 | WEEK 51 | WEEK 52
Geometry
XXX | NOT DEFINED | 0% | 0
Mesher
XXX | NOT DEFINED | 0% | 0
Optimization
XXX | NOT DEFINED | 0% | 0
Development Platform
XXX | NOT DEFINED | 0% | 0